## Objectives
Project Objectives | Status | Description | Week 2 Checkpoint | Midterm Checkpoint
Understand Objective | Completed
Identify Problem | Completed | Predict which factors are linked to increased COVID 19 cases and deaths, use that to predict the number of cases/deaths by county, state, city, country
Define Modeling Goals | Completed
Determine Processes | Completed
Datasets Tasks:
More Factors | Incomplete | Github repo COVID 19 case, death dataset (US and international), joined with risk factor (poverty, health indicators etc). Working on joining case data with other predictor datasets by county
Data Source? | In Progress
Cleanse/Filter (if necessary) | Completed
Data Governance | In Progress
Pipeline Tasks:
Setup Kafka with Docker or WSU Grid | In Progress | Attempting to confige SparkR, RStudion, and the Grid with the HPC team.
Create the Streams Application | In Progress
Kafka, Zookeeper or Spark and topics are ready | In Progress
Deploying Stream | In Progress
Testing with Final Model | In Progress
Modeling Tasks:
Performance Metric Identify | Completed | Determined metrics to use was training error accracy %, R-Squared, MSE, and RMSE.
Model Development Methodology | In Progress | Created linear regression models in Spark shell (Scala) testing with different predictor factors to compare model fits
Identify/Prepare Finalized Datasets | Completed | Historical COVID 19 and predictor data loaded into pandas dataframe in wayne state grid for model input. Pyspark is unavailable on the grid until later this month
Analyze and Transform Variables. Random Sampling | Completed
Model Selection and Develop Models (Training) | Completed | Need to develop time series models locally (Jupyter notebook) then on grid (Spark shell)
Validate Models (Testing), Optimize and Profitability | Completed | Standardized data from the initial dataset posted by John Hopkins University Github into 1 dataset based on Date, Province State, Country Region, Confirmed, Deaths, Recovered.
Document Methodology and Models | In Progress
Implement Models | In Progress
Monitoring and Performance Tracking | In Progress
Visualization Tasks:
Scatter Plots | Completed
Bar Plots | Completed
Line Plots | Completed
Heatmaps | Completed
Other Plots/Graphs | Completed
Customizing titles and axis | Completed
Dashboard Tasks:
UI configuration | Completed
Server configuration | Completed
Global setup | Completed
CSS style | Completed
Tableau migration | Completed